## Sheet1
Stock Viewer Backlog
Members: | Ajay Salh
Task | Description | Priority | Member | Status | Start Date | Complete Date | Comments
Brainstorm/Planning | Brainstorm core concepts, research APIs, divide project into parts. Big picture planning. | 4 | Ajay Salh | Completed | 2021-03-07 | 2021-05-07
Begin Coding | Code basic UI elements/setup layouts/activities | 4 | Ajay Salh | Completed | 2021-05-07 | 2021-05-08
Main Activity/NavBar | Setup navigation bar and begin main activity. | 4 | Ajay Salh | Completed | 2021-05-08 | 2021-05-09
Use API | Learn API calls and how to parse JSON responses | 4 | Ajay Salh | Completed | 2021-05-08 | 2021-05-09
Graph | Learn how to graph data and display it | 4 | Ajay Salh | Completed | 2021-05-09 | 2021-05-09
Implement Crypto | Implement crypto searches | 4 | Ajay Salh | Completed | 2021-05-09 | 2021-05-09
Start Watchlist | Begin working on watchlist feature | 4 | Ajay Salh | Completed | 2021-05-10 | 2021-05-10
RecyclerView | Work on recycler view for watchlist | 4 | Ajay Salh | Completed | 2021-05-10 | 2021-05-10
Content Provider/DB | Setup DB for watchlist | 4 | Ajay Salh | Completed | 2021-05-10 | 2021-05-10
Extend Dataset | Implement more time periods for graph | 4 | Ajay Salh | Completed | 2021-05-10 | 2021-05-11
Optimization | Do more multithreading if possible, try to lessen load on main thread | 4 | Ajay Salh | Completed | 2021-05-10 | 2021-05-11
Debug | Try to break the app and implement more error checking | 4 | Ajay Salh | Completed | 2021-05-11 | 2021-05-11
Final Touches | Make last adjustments and touches, fix UI things | 4 | Ajay Salh | Completed | 2021-05-12 | 2021-05-16

## Utils (hidden)
Priority | Status | Member | All | Ajay Salh
1 | Waiting
2 | Not Started
3 | In Progress
4 | Completed